## implementation checklist
CHG No. | Databases | Server | Database | Object | DEV resource | Dev Completion | UAT resource | UAT completion | PROD resource | Prod Completion | Script | Comments
CHG No. | Logins/Roles | Server | Database | Object | Dev Resource | Dev Completion | UAT resource | UAT completion | PROD Resource | Prod Completion | Script | Comments
CHG No. | Table Modifications | Server | Database | Object | Dev Resource | Dev Completion | UAT resource | UAT completion | PROD Resource | Prod Completion | Script | Comments
CHG No. | Table Creations | Server | Database | Object | Dev Resource | Dev Completion | UAT resource | UAT completion | PROD Resource | Prod Completion | Script | Comments
SC113 | New Table | DEV: devds14 UAT: spin35, spin41,spin51 -- Sync all QA testbeds PROD: psybspin01 | logd1_loginprofiles | application_function | JF | 2016-05-05 | JG | 2016-05-08 |  |  | \\fleet.ad\data\Data4\VMSSHARE\ITS\DM\SCRIPTS\F139\SC 113\Create Table application_function.ddl
CHG No. | Index Creation | Server | Database | Object | Dev Resource | Dev Completion | UAT resource | UAT completion | PROD Resource | Prod Completion | Script | Comments
CHG No. | User Messages | Server | Database | Object | Dev Resource | Dev Completion | UAT resource | UAT completion | PROD Resource | Prod Completion | Script | Comments
CHG No. | Replication | Server | Database | Object | Dev Resource | Dev Completion | UAT resource | UAT completion | PROD Resource | Prod Completion | Script | Comments
SC113 | Create Ref def | edb51 <==> spin51 psybedb01 <==> psybspin01 | N/A | application_function | N/A | N/A | AP | 2017-01-23
SC113 | Create Ref def | edb51 <==> spin51 psybedb01 <==> psybspin01 | N/A | application | N/A | N/A | [5 empty] | Replication should be enable in QA environment same as it is in PROD
SC113 | Create Ref def | edb51 <==> spin51 psybedb01 <==> psybspin01 | N/A | parent_function | N/A | N/A | [5 empty] | Replication should be enable in QA environment same as it is in PROD
SC113 | Create Ref def | edb51 <==> spin51 psybedb01 <==> psybspin01 | N/A | user_function | N/A | N/A | [5 empty] | Replication should be enable in QA environment same as it is in PROD
SC113 | Create Ref def | edb51 <==> spin51 psybedb01 <==> psybspin01 | N/A | login_profile | N/A | N/A | [5 empty] | Replication should be enable in QA environment same as it is in PROD
SC113 | Create Ref def | edb51 <==> spin51 psybedb01 <==> psybspin01 | N/A | phh_login_access | N/A | N/A | [5 empty] | Replication should be enable in QA environment same as it is in PROD
SC113 | Create Ref def | edb51 <==> spin51 psybedb01 <==> psybspin01 | N/A | login_pswrd_status | N/A | N/A | [5 empty] | Replication should be enable in QA environment same as it is in PROD
CHG No. | Trigger Creation | Server | Database | Object | Dev Resource | Dev Completion | UAT resource | UAT completion | PROD Resource | Prod Completion | Script | Comments
CHG No. | Stored Procedure Migrations | Server | Database | Object | Dev Resource | Dev Completion | UAT resource | UAT completion | PROD Resource | Prod Completion | Script | Comments
| Data load | DEV: devds14 UAT: spin35, spin41,spin51 -- Sync all QA testbeds PROD: psybspin01 | spin_north_america | p_cde_get_users | JF | 2016-05-05 | JG | 2017-01-24 |  |  | \\fleet.ad\data\Data4\VMSSHARE\ITS\DM\SCRIPTS\F139\SC 113\p_cde_get_users.sql
CHG No. | View Creations | Server | Database | Object | Dev Resource | Dev Completion | UAT resource | UAT completion | PROD Resource | Prod Completion | Script | Comments
| Recreate View | DEV: devds14 UAT: spin35, spin41,spin51 -- Sync all QA testbeds PROD: psybspin01 | spin_north_america | asset_core_enroll | JF | 2016-05-05 | JG | 2017-01-24 |  |  | \\fleet.ad\data\Data4\VMSSHARE\ITS\DM\SCRIPTS\F139\SC 113\spin_asset_core_enroll.sql
CHG No. | Data Loads | Server | Database | Object | Dev Resource | Dev Completion | UAT resource | UAT completion | PROD Resource | Prod Completion | Script | Comments
| Data load | DEV: devds14 UAT: spin35, spin41,spin51 -- Sync all QA testbeds PROD: psybspin01 | trnd1_spin_work | core_data_user_profiles | JF | 2016-05-05 | JG | 2017-01-24 |  |  | \\fleet.ad\data\Data4\VMSSHARE\ITS\DM\SCRIPTS\F139\SC 113\core_data_user_profiles.sql
CHG No. | Grants | Server | Database | Object | Dev Resource | Dev Completion | UAT resource | UAT completion | PROD Resource | Prod Completion | Script | Comments